## Cover
Risks, Action Items, Issue, and Decisions (RAID) Log
Version: | 4
Team Members | Vedika Shenoy, Andrew Mauch, Aditi Shrivastava, Russel Stein

## Doc Control Info
Document Control Information
Document Information
Document Identification |  | Risk, Action, Issues and Decision Log for Team 4
Document Name |  | Team RAID Log
Project Name |  | TOWARDS RESILIENCY: AN OVERVIEW OF NATIONAL RESOURCES AVAILABLE TO SMALL BUSINESSES
Client |  | Syracuse University
Document Author |  | Vedika Shenoy, Andrew Mauch, Aditi Shrivastava, Russel Stein
Document Version |  | 4
Document Status |  | Closed
Date Released |  | 2019-11-26
Document Edit History
Version | Date | Additions/Modifications |  | Prepared/Revised By
1 | 2019-10-20 | Initial RAID-log drafted |  | Aditi
1.1 | 2019-10-26 | Revised RAID Log |  | Russell
2 | 2019-10-27 | Revised RAID Log |  | Aditi
2.1 | 2019-10-28 | Revised RAID Log |  | Vedika
3 | 2019-11-03 | Revised RAID Log |  | Russell
3.1 | 2019-11-03 | Revised RAID Log |  | Vedika
4 | 2019-11-26 | Final RAID Log |  | Vedika
Document Review/Approval History
Date | Name |  | Organization/Title |  | Comments
2019-10-20 | Aditi |  | Syracuse University
2019-10-20 | Vedika |  | Syracuse University
2019-10-26 | Russel |  | Syracuse University
2019-10-27 | Aditi |  | Syracuse University
2019-11-03 | Russell |  | Syracuse University
2019-11-03 | Vedika |  | Syracuse University
2019-11-26 | Vedika |  | Syracuse University
Distribution of Final Document
The following people are designated recipients of the final version of this document:
Name |  | Organization/Title
Russell Stein |  | Consultant
Aditi Shrivastava |  | Consultant
Vedika Shenoy |  | Consultant
Andrew Mauch |  | Consultant
Dr Michelle Kaarst Brown |  | Team Lead
C

## Risks Log
[10 empty] | Risk Severity Scoring: | Low = 0-5
Risks Log | [10 empty] | Medium = 6-12
High =13-25
Risk Summary | [13 empty] | Risk Details | [8 empty] | Risk Response | [5 empty] | Additional Notes | References
Risk #* | Type | Status* | Created By* | Created On* | Assigned To* | Priority* | Type* | Sub Type | Probability/ Likelihood (A)* | Impact (B)* | Severity | Score (A*B) | Description* | Identified On* | Date Due* | Source* | Risk Impact* | Release | Team | Phase | Thread | Stakeholders | Escalation Level | Risk Response | Response Plan | Risk Contingency Plan | Issue # | Closure Criteria | Notes | Reference Materials
1 | Internal | Closed | Aditi | 2019-10-18 | All Team | Medium | Area of Expertise | Lack of required knowledge | 5 | 3 | Medium | 15 | Team does not have the required research experience | 2019-10-18 | 2019-10-28 | Weekly Meeting | This may lead to project delays and increased number of errors as the team members lack the requisite knowledge | [6 empty] | Mitigate | The team should study more about the project and try to acquiant themselves with required expertise
2 | Internal | Closed | Aditi | 2019-10-18 | All Team | High | Scheduling | Conflict in Timings | 5 | 4 | Medium | 20 | Each of us have different schedules and it may be challenging to get on the same page | 2019-10-18 | 2019-10-25 | Weekly Meeting | This would lead to lag in project timeline and scheduling | [6 empty] | Mitigate | The team sould prepare a meeting schedule and delegate responsibilities equally. Decision #1 is taken in response and the team has consolidated a meeting day every week
3 | Internal | Closed | Aditi | 2019-10-18 | All Team | High | Project Initiation | Unclear Project expectations | 4 | 4 | High | 16 | The project expectations are not verified at this stage so that which could lead to ambiguities and delay. | 2019-10-18 | 2019-10-25 | Weekly Meeting | This would result in the confusion and thus creating project disruption due to lack of direction. | [6 empty] | Mitigate | The team should set-up meeting with the client and send the project porposal as soon a spossible
4 | Internal | Closed | Aditi | 2019-10-18 | All Team | Medium | Communication | Communication problem with client | 3 | 3 | Medium | 9 | Absence of fixed meeting schedule can lead to disruption in communication with the client | 2019-10-18 | 2019-10-22 | Weekly Meeting | Communication disruption with the client would result in mis-aligned project goals and development updates | [6 empty] | Mitigate | The team should contact the client for setting-up project meetings with them
5 | Internal | Closed | Aditi | 2019-10-18 | All Team | High | Cost Contraint | Limited resources available for free/low costs | 3 | 4 | High | 12 | The project requires resources that can be accesed and retreived by small business and hence cost contraint on resource accessibility wil be a problem | 2019-10-18 | 2019-10-25 | Weekly Meeting | This will put a constraint on the type of resources the team can gather for small business | [6 empty] | Mitigate | The team should determine the costs of the project and consult with client if they could include monetized resources
6 | Internal | Closed | Aditi | 2019-10-27 | All Team | High | Relevancy Constraint | Universally prevelant resources are not applicable | 3 | 3 | Medium |  | The project requires resources that are relevant to small businesses and therefore the well-strcutured ERM reports of large companies are not useful. | 2019-10-27 | 2019-10-20 | Resource research | This would lead to lower amount of high quality resources | [6 empty] | Mitigate | The team should focus on doing a thorough research of avavailable national resources for finding verified and useful resources
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Action Items Log
Action Items Log
Summary | [7 empty] | Details | [11 empty] | Notes | References
Action Item #* | Type | Status* | Created By* | Assigned To* | If External, Deloitte POC | Priority* | Action Item Title* | Identified On* | Due Date* | Source | Action Item Detailed Description* | Release | Team | Phase | Thread | Stakeholders | Action Taken | Closed Date | Action Item Age | Notes | Reference Materials
1 | Internal | Closed | Aditi | Vedika | Binita | Low | Communication methods | 2019-10-17 | N/A | Decision #4 | Keep in contact with Binita on updates, questions, feedback | [5 empty] | Vedika contacted Binita, updated her about the meeting timing and scheduled an introduction meeeting | 2019-10-16
2 | Internal | Closed | Aditi | Vedika, Andrew |  | Medium | Test Zoom | 2019-10-18 |  |  | Make sure everyone has access to Zoom | [5 empty] | Vedika and Andrew cordinated and checked if Zoom works for the team to conduct remote meetings | 2019-10-18
3 | Internal | Closed | Aditi | Vedika, Andrew, Aditi, Russell | Binita | High | Meeting plan | 2019-10-18 | N/A |  | Planning the time for meetings with Binita so all members can be present | [5 empty] | The team cordinated and decided on a time for a introduction meeting with Binita | 2019-10-17
4 | Internal | Closed | Aditi | Aditi |  | Medium | Create a shared google project repository | 2019-10-16 |  | Decision #5 | Create a central repository to hold team documents, resources, and other related files | [5 empty] | Aditi created a google folder to update the research documents the team finds in the process | 2019-10-20
5 | Internal | Closed | Aditi | Aditi |  | High | Update Blackboard | 2019-10-18 |  |  | Assign a team member the responsibility to update RAID logs on Blackboard | [5 empty] | Aditi is responsible for updating the first draft of RAID log on Blackboard | 2019-10-20
6 | Internal | Closed | Aditi | Vedika, Russell, Andrew, Aditi |  | High | Team Communication | 2019-10-16 |  | Decision #2 | Decision of communication mode within the team | [5 empty] | The team discussed about the communication method and decided to use whatsapp | 2019-10-16
7 | Internal | Closed | Aditi | Aditi |  | High | Minutes of Meeting | 2019-10-16 |  | Decision #3 | Assign a team member to take the minutes of meeting | [5 empty] | Aditi will take MOM for every meeting for the project | 2019-10-20
8 | Internal | Closed | Aditi | Russel, Vedika |  | High | Upload and refine deliverable | 2019-10-19 |  |  | Assign the responsibility of refining the project status report to 2 memebers | [5 empty] | Vedika and Russel will refine the project status report and Vedika will update it on Blackboard | 2019-10-18
9 | Internal | Closed | Aditi | Vedika, Russell, Andrew, Aditi |  | High | Upload and refine deliverable | 2019-10-18 |  |  | Team drafted the proposal together and assigned a team member to revise and upload it. | [5 empty] | Version 1 of Project Proposal will be edited by the team and uploaded on Blackboard by Vedika. She will also e-mail the proposal to Michelle on behalf of the team | 2019-10-18
10 | Internal | Closed | Aditi | Aditi |  | High | Revise Proposal | 2019-10-20 |  |  | Assign a team member to revise the proposal based on Michelle's review | [5 empty] | Version 2 of Project Proposal will be editedand uploaded on Blackboard by Aditi | 2019-10-20
11 | Internal | Closed | Russell | Vedika, Russell, Andrew, Aditi |  | High | Remote Meeting | 2019-10-24 |  |  | Team decided to conduct remote meetings for the weekend | [5 empty] | Due to the amount of research needed to be done this weekend the team thought it would be best to conduct remote meetings and research from home. | 2019-10-24
12 | Internal | Closed | Aditi | Vedika, Russell, Andrew, Aditi |  | High | Research segregation | 2019-10-26 |  | Decision #7 | The team decided to divide the steps involved in ERM cycle | [5 empty] | The ERM cycle consists of several steps and the team decided to divide them amongst the members for better and thorough research | 2019-10-27
13 | Internal | Closed | Russell | Vedika, Russell, Andrew, Aditi |  | Medium | Remote Meetings | 2019-10-31 |  | Decision #8 | Team 4 will conduct multiple remote meetings over the weekend of 11/1 in order to discuss resources and consolidate research. | [5 empty] | Because some team members were away from campus this weekend we thought it would be best to conduct remote meetings given the unique circumstances. | 2019-11-03
14 | Internal | Closed | Russell | Vedika | Binita | High | Advisory Meeting | 2019-10-31 |  | Decision #13 | We have not spoken to Binita in over a week regarding our project status so we would like to talk with her and ask her questions regarding both our research methods as well as other general concerns, | [5 empty] | Vedika sent an email to get in touch with Binita in order to discuss our current project status. | 2019-11-03
15 | Internal | Closed | Russell | Vedika |  | High | Research Consolidation | 2019-11-03 |  | Decision #9 | By creating a google drive our team will be able to regularyly upload resources which we find while conducting research, this also allows us to review each others resources as well. | [5 empty] | Vedika create a google drive in order to consolidate all resources. | 2019-11-03
16 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | Resource prioritization | 2019-11-03 |  | Decision #10 | The resources must be prioritized according to the best quality. | [5 empty] | The resources were prioritized according to best quality. | 2019-11-03
17 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | Synthesis of resources | 2019-11-03 |  | Decision #11 | The resources must be synthesized according to application and viability. | [5 empty] | The resources were synthesized according to application and viability. | 2019-11-03
18 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | Finalization of resources | 2019-11-03 |  | Decision #12 | The relevant resources must be finalized for the project. | [5 empty] | The relevant resources were finalized for the project. | 2019-11-03
19 | Internal | Closed | Vedika | Vedika | Binita | High | Advisory Meeting | 2019-11-07 |  | Decision #14 | We have not spoken to Binita in over a week regarding our project status so we would like to talk with her and ask her questions regarding tips on giving better presentation. | [5 empty] | Vedika sent an email to get in touch with Binita. | 2019-11-07
20 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | 1st revision of key findings and its summary | 2019-11-08 |  |  | The 1st revision of resources is needed to find the relevant findings and summarize it in the presentation, | [5 empty] | 1st revision of resources completed. | 2019-11-08
21 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | 2nd revision of key findings and its summary | 2019-11-09 |  |  | The 2nd revision of resources is needed to find the relevant findings and summarize it in the presentation, | [5 empty] | 2nd revision of resources completed. | 2019-11-09
22 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | Formulation of next steps | 2019-11-09 |  | Decision #15 | The next step formulation is an important input for the project as it suggests how the client can move ahead with the resources provided. | [5 empty] | The next steps were formulated by the team. | 2019-11-09
23 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | Annotated bibliography | 2019-11-09 |  | Decision #16 | The annotated bibliography of the resources needs to be created. | [5 empty] | The annotated bibliography was created by the team. | 2019-11-09
24 | Internal | Closed | Vedika | Vedika, Aditi, Russell |  | High | Live Rehearsal Presentation | 2019-11-12 |  | Decision #17 | The live rehearsal presentation needs to be created. | [5 empty] | The live rehearsal presentation was created by the team. | 2019-11-12
25 | Internal | Closed | Vedika | Vedika, Aditi |  | High | 1st revision of Presentation | 2019-11-14 |  |  | The presentation needs to be changed according to Michelle's feedback. | [5 empty] | The revision was made to the presentation. | 2019-11-14
26 | Internal | Closed | Vedika | Vedika, Aditi |  | High | 2nd revision of Presentation | 2019-11-17 |  |  | The presentation needs to be changed according to Michelle's feedback. | [5 empty] | The revision was made to the presentation. | 2019-11-17
27 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | High | Final Presentation to the client | 2019-11-19 |  |  | The final presentation needs to be given to the client along with a Q&A session. | [5 empty] | The final presentation was given to the client along with Q&A session. | 2019-11-19
28 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | Critical | Delivery of Physical Binder | 2019-11-19 |  | Decision #18 | The physical binder of resources must be handed over to the client. | [5 empty] | The physical binder was handed over to the client. | 2019-11-19
29 | Internal | Closed | Vedika | Vedika, Russell, Andrew, Aditi |  | Critical | Deliver of digital copy of resources | 2019-11-19 |  | Decision #19 | The digital copies of the resources must be handed over to the client in a flash drive. | [5 empty] | The digital copies of the resources were handed to the client, | 2019-11-19
Sample Data

## Issue Log
Issues Log
Summary | [16 empty] | Resolution | [5 empty] | Notes | References
Issue #* | Type | Status* | Created By* | Created On* | Assigned To* | Priority* | Type* | Sub Type | Description* | Due Date* | Detailed Description* | Release | Team | Phase | Thread | Stakeholders | Escalation level | Resolution* | Closed Date | Change Request # | Issue Age | Closure Criteria | Notes | Reference Materials | NOTE: Calculation in this column is used for Stats Report
1 | Internal | Closed | Aditi | 2019-10-17 | Russell | Medium | Scheduling | Team member unavailable | Russell had a scheduling conflict with another meeting | 2019-10-18 | Russel will be traveling during scheduled meeting with Binita | [6 empty] | The team decided to conduct the meeting remotely on Zoom call
2 | Internal | Closed | Aditi | 2019-10-17 | Vedika | Medium | Scheduling | Team member unavailable | Vedika will be out-of-town | 2019-10-18 | Vedika will be travelling on the weekend (19th & 20th Oct) and will be available on call/texts | [6 empty] | The team will provide her updates and she will finish her tasks before the weekend. Also, she will be available on e-mails for further project discussion
3 | Internal | Closed | Aditi | 2019-10-18 | Aditi | Medium | Scheduling | Team member unavailable | Aditi will be out-of-town | 2019-10-20 | Aditi will be in NYC from Nov 1-5 and will not be able to attend team meetings | [6 empty] | The team will provide her update on the project and another teammemeber will be responsible for taking MOM
4 | Internal | Closed | Russell | 2019-11-03 | Russell | Medium | Scheduling | Team Member unavailable | Andrew will be out-of-town | 2019-11-03 | Andrew will not be around the Syracuse Campus from 10/31 to 11/3, and will be available via call or text | [6 empty] | Andrew will still work remotely on the project, gathering research for his respective topic and adding it to our google drive.

## Decision Log
Decision Log
Decision Summary | [5 empty] | Reference
Decision #* | Decision Description* | Decision Approval Authority (Name and Title)* | Decision Date* | Title and Location of Supporting Materials* | Feedback/History
1 | Weekly meeting scheduled on Friday at 5 PM | Vedika, Russell, Andrew, Aditi | 2019-10-18 |  | This decsion is taken in response to mitigate risk #2 | 38
2 | Commmunication channel for the team would be whatsapp | Vedika, Russell, Andrew, Aditi | 2019-10-18 |  | Action #6 is taken in response to this decision | 1900-02-06
3 | Aditi is assigned to take the Minutes of Meeting. | Vedika, Russell, Andrew, Aditi | 2019-10-18 |  | Action #7 is taken in response to this decision
4 | Vedika is assiged to communicate amd email Binita on the behalf of the team | Vedika, Russell, Andrew, Aditi | 2019-10-18 |  | Action #1 is taken in response to this decision
5 | The team decided to create a google folder to store and share the research dcouments | Vedika, Russell, Andrew, Aditi | 2019-10-18 |  | Action #4 is taken in response to this decision
6 | Team 4 will conduct research in regards to the project in order to find reliable sources and documents | Vedika, Russell, Andrew, Aditi | 2019-10-24 |  | Action #11 is taken in response to this decision
7 | Each team member picked a step in the ERM cycle such preparedness, disaster recovery etc. for in regards to the project, leading to no overlapping research | Vedika, Russell, Andrew, Aditi | 2019-10-24 |  | Action #12 is taken in response to this decision
8 | Team 4 will conduct remote meetings over the weekend of November 1st in order to gather research for the specific topic | Vedika, Russell, Andrew, Aditi | 2019-10-31 |  | Action #13 is taken in response.
9 | Vedika will creat a google drive in order to keep track of all the resources we gather, this also allows us to keep all our resources organized and in one place | Vedika, Russell, Andrew, Aditi | 2019-11-03 |  | Action #15 is taken in response.
10 | Team decided that the relevant resources need to be prioritized. | Vedika, Russell, Andrew, Aditi | 2019-11-03 |  | Action #16 is taken in response.
11 | Team decided that the resources need to be synthesized. | Vedika, Russell, Andrew, Aditi | 2019-11-03 |  | Action #17 is taken in response.
12 | The team decided that the resources need to be prioritized. | Vedika, Russell, Andrew, Aditi | 2019-11-03 |  | Action #18 is taken in response.
13 | Team 4 decided to contact Binita for her guidance. | Vedika, Russell, Andrew, Aditi | 2019-11-03 |  | Action #14 is taken in response.
14 | Team 4 decided to contact Binita for her guidance. | Vedika, Russell, Andrew, Aditi | 2019-11-07 |  | Action #19 is taken in response.
15 | The team decided to formulate next steps for the client. | Vedika, Russell, Andrew, Aditi | 2019-11-09 |  | Action #22 is taken in response.
16 | Team decided to develop the annotated bibliography | Vedika, Russell, Andrew, Aditi | 2019-11-09 |  | Action #23 is taken in response.
17 | Team decided to develop the presentation. | Vedika, Russell, Andrew, Aditi | 2019-11-12 |  | Action #24 is taken in response.
18 | Team decided to deliver the physical binder. | Vedika, Russell, Andrew, Aditi | 2019-11-19 |  | Action #28 is taken in response.
19 | Team decided to deliver the soft copies of the resources in a flash drive. | Vedika, Russell, Andrew, Aditi | 2019-11-19 |  | Action #29 is taken in response.